## Sheet1
ReqNo | Requirement | Description | Priority | Asignee | Status
1 | Website
1.1 | Website Implemented using CMS
1.1.1 | Customise CSS
1.1.2 | Customise Control
1.2 | Paypal integration
1.2.1 | Charity should provide unique link to their PayPal accunt
1.2.2 | Dynamic UI | Website should rescale to be displayed on both phones&tablets
Events
Add, Edit, View Events
Forms
Confirm Form
Generate Form (includes Save Form)
Only admin can edit
Login
Password Generation/Confirmation/Recovery
Username Registration/Recovery
Charity Worker
Login
View forms
Donations
Populate forms
Search
1.3 | Administration Panel
1.3.1 | Insert New Users
Allocate Users Priviledges
History
Password Reset
Approve/Decline Requests
1.3.2 | Generate Reports
1.4 | REST Web Service
1.4.1 | Insert and Select operations
2 | Android
2.1 | Application accessible from Mobile Phones and Tablets | UI should rescale to be displaied on both Phones&Tablets
2.2 | Offline SQLite Integration | Prototype to integrate the system for offline use when online DB not available.
2.3 | HTML5+CSS caching | Cache website for offline use. Implement prototype first.
3.1 | Database
3.1.1 | SQL Database
3.1.1.2 | User
3.1.1.3 | Privileges
3.1.1.4 | Charity Details
3.1.2 | DB Hosting & DB Connectons with Android, Website, Web Service
3.1.3 | DB Schema Design in MySQL | should contain Tables&Relationships
3.1.3.1 | DB Schema for the System | Tables for Users, Privileges, Charity Details , Constaints and Relationships, Primari&Foreign Key
3.1.3.2 | DB Schema for genereic form builder | Maintain flexibility for reporting purposes
3.2 | Reporting and Statistics
3.2.1 | Exporting reports/statistics to Excel/R
3.2.1.1 | Integrate Reporting&Statistics API for Java with DB
3.2.2 | Generate SQL according to CMS Customisations
3.2.3 | Create Query Builder Functionality
4 | Integration
4.1 | Web Service Integration
4.2 | Android - DB Integration
4.3 | Web Site - DB Integration
5.1 | Testing
5.1.1 | Unit testing | JUnit
5.1.2 | Stress testing (JMeter) | JMeter
5.1.2 | Android testing | Test application on tables&phones. Possible HTML5 testing
5.1.3 | Selenium testing | Automated testing for the website. Possible HTML5 testing
5.2 | Documentation
5.2.1 | Design Patterns & System Architecture | Document all design patterns used and their impact on the overall architecture of the application
5.2.2 | Implementation Decisions | Document all implementation decisions made by the team
5.2.3 | Testing Procedures | Document all testing procedures used and draw conclusions based on their results
5.2.4 | Testing Coverage | Document testing coverage achieved and draw conclusions regarding the relevance of the testing performed
5.2.5 | User Manual | Produce an introduction to using the application. Include all important features and step by step guides
5.2.6 | Technical Manual | Produce an extensive documentation on what tools have been used, what versions and how to set up the Dev Env